## Sheet1
Area | What tools can we use to understand our current situation? | What is our current situation? | What are our objectives? These objectives are outlined in pages 14-35 in the Brent Schools Climate Action Guide | What specific actions can we take to achieve this objective? | Who will make this happen? | How will this be measured/reviewed? | Who will be responsible for measuring/reviewing this? | Time frame | Estimated cost | What funding can we use or apply for to help make this happen?
Decarbonisation
Energy | Keep Britain Tidy’s Count Your Carbon tool - https://www.countyourcarbon.org/home/ | In 2024/2025 spent £12,181.76 on electricity. Predicted spend in 25/26 is £9,991.93. In 2024/25 spend on Gas was £8653.65. Predicted spend in 2025/26 is £10,042.94. We have a boller that is over 20 years old that is inefficient. We have solar panels that need to be repaired and maintained. We have a aging boiler system. Water usuage | Increase energy-efficiency of the school site | Bolier to be changed | Vertas property management services | Reviewed once a term in F&F commmiteee | Headteacher/Chair of F&F comittee | 2026-2027 | 40000 | CYP from SCC
| Sign up to Climate Friendly Schools for FREE and use their Energy Audit tool - https://www.climatefriendlyschools.org.uk/theme/climate-friendly-energy-audit/ |  | Increase use of renewable energy sources on the school site | Current solar panels to be serviced and identify how the energy can benefit the school | F&F team working with | Reviewed once a term in F&F commmiteee | Headteacher/Chair of F&F comittee | 2027 | Annual £200 | to be included in school maintennace budget
| Recommendation Report from your Display Energy Certificate [DEC] |  | Create a positive culture and influence behaviour change around reducing energy use | Turning off lights in the classroom/offices when not in use. To update all taps in school to stop water leakage and to change water fountains in school. Start to replace lights with Led lights | BCPS facilities team | Reviewed once a term in F&F commmiteee | Headteacher/Chair of F&F comittee | 2027 | £500 annual | to be included in school maintennace budget
Brent's Schools Survey Template - https://www.brent.gov.uk/neighbourhoods-and-communities/community-priorities/climate-emergency/supporting-communities/climate-action-in-schools
Travelling to school |  | Majority of pupils walk to school | Encourage journeys taken by walking, cycling and public transport | Meeting with School Active Travel Officer to set us a school walking bus | Volunteer parents | Reviewed once a term in F&F commmiteee | Headteacher/Chair of F&F comittee | 2025 | 0 | We will use high vis jackets that are available in school
| BBC Pollution levels tool - https://www.bbc.co.uk/news/science-environment-42566393 |  | Create a positive culture and behaviour change around transport use | For school trips consider number of trips that require a coach and which trips pupils can walk to | BCPS facilities team | Reviewed once a term in F&F commmiteee | Headteacher/Chair of F&F comittee | 2025 | 2000 | School subsidise and parent cost of transport for trips
Adaptation and resilience | UK Gov Flood Risk Map - https://flood-map-for-planning.service.gov.uk/ | Improved wifi has reduced risk of school closures | Reduce the risk of school closures and disruption to exams and lessons | We have upgraded our school phone lines to use a cloud based telephone system | BCPS facilities team | Reviewed once a term in F&F commmiteee | Headteacher/Chair of F&F comittee | 2024 | £91 monthly | to be included in school maintennace budget
|  |  | Protect staff and students from the risks of extreme weather | we have updated our cloud based broadband and wifi | BCPS facilities team | Reviewed once a term in F&F commmiteee | Headteacher/Chair of F&F comittee | 2024 | £50 BT bill monthly | to be included in school maintennace budget
|  |  | Ensure school sites can cope with more extreme weather |  |  | Reviewed once a term in F&F commmiteee | Headteacher/Chair of F&F comittee
Biodiversity | Sign up to Education Nature Park - https://www.educationnaturepark.org.uk/user/register | School Garden in place and we have a volunteer gardener who works with each class a half term | Increase or enhance green space on the school site or nearby | continue to develop the school garden and create compost area | BCPS facilities team | Reviewed once a term in F&F commmiteee | Headteacher/Chair of F&F comittee | 2026 | 100 | to be included in school maintennace budget
| Education Nature Park's tools for exploring your school site - https://www.educationnaturepark.org.uk/resources/Explore%20Your%20School%20Site |  | Connect students and staff with nature | Science - all pupils to use garden to grow food | BCPS facilities team | Reviewed once a term in F&F commmiteee | Headteacher/Chair of F&F comittee | 2025 | £50 for seeds | donations
| RSPB birdwatch - https://www.rspb.org.uk/whats-happening/get-ready-for-big-schools-birdwatch |  | Develop knowledge and skills relating to biodiversity and growing/gardening |  |  | Reviewed once a term in F&F commmiteee | Headteacher/Chair of F&F comittee
Pupil surveys
Waste and consumption | Plastic Free July's bin audit tool - https://www.plasticfreejuly.org/get-involved/what-you-can-do/bin-audit/ | We will have food waste bins in lunchhall and all classrooms. Will have recycling ang general waste bin in all classroom | Reduce the amount of waste produced on the school site | Food waste bins have been ordered. Lunchtime catering team will be managing food waste. | BCPS facilities team | Reviewed once a term in F&F commmiteee | Headteacher/Chair of F&F comittee | 2025 | £600 contract for food waste (annual) | to be included in school maintennace budget
Sign up to Climate Friendly Schools for FREE and use their Food Audit tool - https://www.climatefriendlyschools.org.uk/theme/climate-friendly-food-audit/
| Sign up to Climate Friendly Schools for FREE and use their Consumption Audit tool - https://www.climatefriendlyschools.org.uk/theme/climate-friendly-consumption-audit/ |  | Influence behaviour changes and create a positive culture around reducing waste and overconsumption of resources | Contact with local council to order a school food waste bin for the whole school. Audit completed to ensure all classes/offices have a blue recycle bin and general waste bin. | Babergh and BCPS facilities team | Reviewed once a term in F&F commmiteee | Headteacher/Chair of F&F comittee | 2025 | Food compost caddy £9 each ( purchased 9 for rooms in school) Also compost bin liners | to be included in school maintennace budget
|  |  | Develop knowledge around waste and resource overconsumption and how they link to the climate and ecological emergency | With school council promote use of general waste bin and recycling bin | BCPS facilities team | Reviewed once a term in F&F commmiteee | Headteacher/Chair of F&F comittee | 2025
Climate education and green skills | Teach the Future Tracked Changes Project - https://www.teachthefuture.uk/tracked-changes-project | Limited curriculum on climate education | Support teachers with embedding climate education in their existing curriculum | Map curriculum to evidence the teaching of climate education escpecially in science and RSE | Curriculum leaders | Reviewed once a term in Curriculum commmiteee | Headteacher/Chair of Curriculm comittee | 2026-28 | TBC | to be included in school ESS budget
|  |  | Develop teachers’ confidence in teaching about climate change | CPD for teachers on climate chanage | Curriculum leaders | Reviewed once a term in Curriculum commmiteee | Headteacher/Chair of Curriculm committee | 2026-28 | TBC | to be included in school ESS budget
|  |  | Develop students’ knowledge and skills relating to climate change | map skills and knowledge that pupils need to develop | Curriculum leaders | Reviewed once a term in Curriculum commmiteee | Headteacher/Chair of Curriculm committee | 2026-28 | TBC | to be included in school ESS budget
| Brighton and Hove's Our City Our World conceptual mapping tool - https://www.ourcityourworld.co.uk/wp-content/uploads/2023/02/Conceptual-Milestones-2.pdf |  | Develop students' knowledge and skills relating to climate justice | map skills and knowledge that pupils need to develop | Curriculum leaders | Reviewed once a term in Curriculum commmiteee | Headteacher/Chair of Curriculm committee | 2026-28 | TBC | to be included in school ESS budget
|  |  | Empower and enable young people to take climate action | map skills and knowledge that pupils need to develop | Curriculum leaders | Reviewed once a term in Curriculum commmiteee | Headteacher/Chair of Curriculm committee | 2026-28 | TBC | to be included in school ESS budget
Green careers |  | limited curriculum on green careers | Develop careers curriculum to include a focus on green careers | CPD for teachers on green careers | Curriculum leaders | Reviewed once a term in Curriculum commmiteee | Headteacher/Chair of Curriculm committee | 2026-28 | TBC | to be included in school ESS budget
|  |  | Empower students by increasing their knowledge and awareness of green careers | map skills and knowledge that pupils need to develop | Curriculum leaders | Reviewed once a term in Curriculum commmiteee | Headteacher/Chair of Curriculm committee | 2026-28 | TBC | to be included in school ESS budget
|  |  | Increase students’ exposure to climate action in the real world | map skills and knowledge that pupils need to develop | Curriculum leaders | Reviewed once a term in Curriculum commmiteee | Headteacher/Chair of Curriculm committee | 2026-28 | TBC | to be included in school ESS budget